## Summary FYs 14-16
REPORTED NUISANCE PROPERTIES FY 2014 - 2016
MAYOR'S OPERTATIONS INNOVATION TEAM
Working Draft
NUISANCE ABATEMENT LOG FYs 14-16
TOTAL PROPERTIES REPORTED | 63
NUMBER OF JOBS TO DATE | 98
NUMBER OF JOBS COMPLETED | 84
TOTAL EXPENSE | 425398.217
NUISANCE ABATEMENT LOG FY 14-15
NUMBER OF JOBS TO DATE | 79
NUMBER OF JOBS COMPLETED | 75
YTD EXPENSE | 367695.497
NUISANCE ABATEMENT LOG FY 15-16
NUMBER OF JOBS TO DATE | 19
NUMBER OF JOBS COMPLETED | 9
YTD EXPENSE | 57702.72

## Reported Nuisance Properties
REPORTED NUISANCE PROPERTIES FYs 2014-2016
Street # | Street Name | City & ZIP | Building Name
0 | Washington Blvd/53rd St/Santa Fe | LA 90058 | vacant lot
0 | Avenue 35 & Pasadena City APN: 5205004900 LA Metro APN: 5205004903 | LA | vacant lot
0 | Browns Canyon Silo APN 2821-002-900 12080 BROWNS CANYON RD | Chatsworth 91311 | vacant lot
300 | Mount Holyoke | LA 90272 | street intersection
361 | S. Hill Street | LA | Bunker Hill - Parcel Y - Angeles Knoll
412 | Paseo Miramar | Pacific Palisades 90272 | vacant lot
421 | Ave 19 | LA 90031 | Old Lincoln Heights Jail
438 | Mesa St | San Pedro 90731 | FS 53
501 | Mesa St | San Pedro 90731 | Neigh Hsng Service of LA
503 | Broad Ave | wilmington 90744 | vacant lot
510 | Venice Blvd | Venice 90291 | vacant lot
520 | Venice way | Venice 90291 | vacant lot
550 | Ramirez St | LA 90012 | LAPD parking lot
610 | California Ave | Venice 90291 | Vera Davis Ctr
749 | Manchester | LA 90044 | FS 57
949 | Carondolet | LA 90006 | vacant lot
956 | 81st St | LA 90044 | APN 6032-005-900 vacant lot
1206 | Vermont |  | FS 13
1269 | Ozeta Terrace (Ozeta & Clark St) | LA 90069 | vacant lot
1309 | Isabel st | LA 90065 | vacant lot
1525 | 103rd St | LA 90002 | FS 65
1631 | E 110TH | LA 90059 | vacant lot
1704 | Jefferson Blvd | LA 90007 | vacant lot
1803 | Arlington | LA | Old Washington Library
2254 | 103rd St | LA 90002 | vacant lot
2916 | Beachwood | Hollywood 90068 | SFR
3233 | Thatcher |  | Sanitation
3311 | Thatcher | Venice 90292 | vacant Street Maintenance yard
3612 | 11th Ave | LA 90018 | SLA Animal Shelter
3642 | Roseview Ave | LA 90065 | vacant lot
3671 | Vermont Ave - South | LA | Bethune Library
4225 | Olive st | LA 90037 | old Junipero Serra Library
4230 | Coldwater Canyon | Studio City 91604 | FS 78
4255 | Olive St | LA 90037 | old Junipero Serra Library
4630 | Griffin Avenue | LA 90031
4958 | Cahuenga | NH 91601
5001 | Balboa Blvd | Encino 91316 | FS 83
5965 | St Andrew Place | LA 90047 | APN 6001-013-906 old temp site for 77th PD
5975 | Western Ave | LA 90047 | vacant lot
6353 | Lindley Avenue | Reseda 91355 | vacant lot APN 2124018905
6621 | Manchester | LA 90045 | FS 5
6621 | W 85TH PL | LA 90045
8100 | Vermont | LA 90044 | vacant lot - Vermont Miracle Park
11514 | Willowbrook | LA 90059 | vacant lot
11950 | Missouri Avenue | LA 90025 | WLA Animal Shelter
12560 | San Fernando Rd | Sylmar 91342 | APN 2506-034-900
14123 | Nordhoff |  | FS 7
15329 | De Pauw | Pacific Palisades 90272 | SFR
15333 | De Pauw | Pacific Palisades 90273 | SFR
15733 | Pacific Coast Hwy | Pacific Palisades 90272 | vacant lot
18777 | Eldeen Drive | Tarzana | vacant lot
22322 | Napa | Chatsworth 91304 | vacant lot
22345 | Malden Avenue | Chatsworth 91304 | vacant lot
11253,11259, 11265, 11273 | Laurie Drive | LA 91604 | vacant lot
3646-3650 | Knobhill | Sherman Oaks | vacant lot
970-1010 | Jefferson Blvd | LA 90011 | Paul Williams/Angelus Funeral Home
| Ave 26 & Lacy | LA | vacant lot
| Tupper & columbus Ave | North Hills | vacant lot
| APN 2784002902. |  | Northridge Metrolink Station
| Ave 49 thru Ave 52 |  | Sycamore Grove Park
| 94th & Broadway |  | APN: 6053-006-926
|  | Chatsworth | Nike Browns Canyon silo
| 4th & Santa Fe | LA 90058 | under the bridge
| 86th St & Broadway | LA | vacant lot
| Tupper & columbus Avenue | North Hills | vacant lot
| Ave 26 & Lacy | LA | vacant+D3:D68 lot
|  | TOTAL REPORTED NUISANCE PROPERTIES | 63
Note on A56: 103059: CD 2 may pay for work. Quote is needed.

## Summary FY14-15
NUISANCE ABATEMENT LOG FY 14-15
NUMBER OF JOBS TO DATE | 79
NUMBER OF JOBS COMPLETED | 75 | 94.94%
NUMBER OF JOBS PENDING | 4
YTD EXPENSE: | 367695.497

## Summary FY15-16
NUISANCE ABATEMENT LOG FY 15-16
NUMBER OF JOBS TO DATE | 19
NUMBER OF JOBS COMPLETED | 9
NUMBER OF JOBS PENDING | 10
YTD EXPENSE: | 57702.72

## Identified Duplicates
0 | Washington Blvd/53rd St/Santa Fe | LA 90058 | vacant lot
0 | Avenue 35 & Pasadena City APN: 5205004900 LA Metro APN: 5205004903 | LA | vacant lot
0 | Browns Canyon Silo APN 2821-002-900 12080 BROWNS CANYON RD | Chatsworth 91311 | vacant lot
300 | Mount Holyoke | LA 90272 | street intersection
361 | S. Hill Street | LA | Bunker Hill - Parcel Y - Angeles Knoll
412 | Paseo Miramar | Pacific Palisades | vacant lot | 6
412 | Paseo Miramar | Pacific Palisades 90272 | vacant lot | 6
421 | Ave 19 | LA | Old Lincoln Heights Jail | 8
421 | Ave 19 | LA | Lincoln Heights jail | 8
421 | Avenue | LA | Lincoln Heights jail | 8
421 | Ave 19 | LA 90031 | Old Lincoln Heights Jail | 8
421 | Ave 19 | LA 90031 | Old Lincoln Heights Jail | 8
421 | Ave 19 | LA | Old Lincoln Heights Jail | 8
421 | Ave 19 | LA | Old Lincoln Heights Jail | 8
421 | Ave 19 | LA 90031 | Old Lincoln Heights Jail | 8
421 | Ave 19 | LA | Old Lincoln Heights Jail | 8
421 | Ave 19 | LA | Old Lincoln Heights Jail | 8
421 | Ave 19 | LA | Old Lincoln Heights Jail | 8
421 | Ave 19 | LA | Old Lincoln Heights jail | 8
421 | Ave 19 | LA | Old Lincoln Heights Jail | 8
438 | Mesa St | San Pedro 90731 | FS 53
501 | Mesa St | San Pedro 90731 | Neigh Hsng Service of LA
503 | Broad Ave | wilmington 90744 | vacant lot
510 | Venice Blvd | Venice 90291 | vacant lot
520 | Venice way | Venice 90291 | vacant lot
550 | Ramirez St | LA 90012 | LAPD parking lot
610 | California Ave | Venice 90291 | Vera Davis Ctr
749 | Manchester | LA | FS 57 | 28
749 | Manchester | LA | FS 57 | 28
749 | Manchester | LA | FS 57 | 28
749 | Manchester | LA | FS 57 | 28
749 | Manchester | LA | FS 57 | 28
749 | Manchester |  | FS 57 | 28
749 | Manchester | LA 90044 | FS 57 | 28
949 | Carondolet | LA 90006 | vacant lot
956 | 81st St | LA 90044 | APN 6032-005-900 vacant lot
1206 | Vermont |  | FS 13
1269 | Ozeta Terrace (Ozeta & Clark St) | LA 90069 | vacant lot
1309 | Isabel st | LA 90065 | vacant lot
1525 | 103rd Street |  | FS 65 | 40
1525 | 103rd St | LA 90002 | FS 65 | 40
1525 | 103rd St | LA 90002 | FS 65 | 40
1631 | E 110TH | LA 90059 | vacant lot
1704 | Jefferson Blvd | LA 90007 | vacant lot
1803 | Arlington |  | Washington Irving Library | 45
1803 | Arlington |  | Old Washington Library | 45
1803 | Arlington | LA | Old Washington Library | 45
2254 | 103rd St | LA 90002 | vacant lot | 48
2254 | 103rd St | LA 90002 | vacant lot | 48
2916 | Beachwood | Hollywood 90068 | SFR
3233 | Thatcher |  | Sanitation
3311 | Thatcher | Venice 90292 | vacant Street Maintenance yard
3612 | 11th Ave | LA 90018 | SLA Animal Shelter | 53
3612 | 11th Ave | LA 90018 | SLA Animal Shelter | 53
3642 | Roseview Ave | LA 90065 | vacant lot
3671 | Vermont Ave - South | LA | Bethune Library | 56
3671 | Vermont Ave - South | LA | Bethune Library | 56
4225 | Olive st | LA 90037 | old Junipero Serra Library
4230 | Coldwater Canyon | Studio City 91604 | FS 78 | 59
4230 | Coldwater Canyon | Studio City 91604 | FS 78 | 59
4255 | Olive St | LA 90037 | old Junipero Serra Library
4630 | Griffin Avenue | LA 90031
4958 | Cahuenga | NH 91601
5001 | Balboa Blvd | Encino 91316 | FS 83 | 64
5001 | Balboa Blvd | Encino 91316 | FS 83 | 64
5001 | Balboa Blvd | Encino 91316 | FS 83 | 64
5001 | Balboa Blvd | Encino 91316 | FS 83 | 64
5965 | St Andrew Place | LA 90047 | APN 6001-013-906 old temp site for 77th PD
5975 | Western Ave | LA 90047 | vacant lot | 69
5975 | Western Ave | LA 90047 | vacant lot | 69
6353 | Lindley Avenue | Reseda 91355 | vacant lot APN 2124018905
6621 | Manchester | LA 90045 | FS 5 | 72
6621 | W 85TH PL | LA 90045 |  | 72
6621 | Manchester | Westchester 90045 | FS 5 | 72
6621 | Manchester | Westchester 90045 | FS 5 | 72
6621 | Manchester | LA 90045 | FS 5 | 72
8100 | Vermont | LA 90044 | vacant lot - Vermont Miracle Park
11514 | Willowbrook | LA 90059 | vacant lot
11950 | Missouri | LA 90025 | Old West Animal Shelter | 79
11950 | Missouri Avenue | LA 90025 | WLA Animal Shelter | 79
12560 | San Fernando Rd | Sylmar 91342 | APN 2506-034-900
14123 | Nordhoff |  | old FS# 7 | 82
14123 | Nordhoff |  | FS 7 | 82
15329 | De Pauw | Pacific Palisades |  | 84
15329 | De Pauw | Pacific Palisades 90272 | SFR | 84
15333 | De Pauw | Pacific Palisades 90273 | SFR | 86
15333 | De Pauw | Pacific Palisades | SFR | 86
15733 | Pacific Coast Hwy | Pacific Palisades 90272 | vacant lot
18777 | Eldeen Drive | Tarzana | vacant lot
22322 | Napa | Chatsworth 91304 | vacant lot
22345 | Malden Avenue | Chatsworth 91304 | vacant lot
11253,11259, 11265, 11273 | Laurie Drive | LA 91604 | vacant lot
3646-3650 | Knobhill | Sherman Oaks | vacant lot
970-1010 | Jefferson Blvd | LA 90011 | Paul Williams / Angelus Funeral | 94
970-1010 | Jefferson Blvd | LA 90011 | Paul Williams/Angelus Funeral Home | 94
970-1010 | Jefferson Blvd | LA |  | 94
| Ave 26 & Lacy | LA | vacant lot
| Tupper & columbus Ave | North Hills | vacant lot
| APN 2784002902. |  | Northridge Metrolink Station
| Ave 49 thru Ave 52 |  | Sycamore Grove Park
| 94th & Broadway |  | APN: 6053-006-926
|  | Chatsworth | Nike Browns Canyon silo
| 4th & Santa Fe | LA 90058 | under the bridge
| 86th St & Broadway | LA | vacant lot
| Tupper & columbus Avenue | North Hills | vacant lot
| Ave 26 & Lacy | LA | vacant lot
TOTAL REPORTED NUISANCE PROPERTIES
Note on A92: 103059: CD 2 may pay for work. Quote is needed.

## FY 14-15
Street # | Street Name | City & ZIP | Building Name | CD | Date of Request | Work Requested | Requested by: | To: CFD | CFD Estimate | Cost | COMPLETED | Date Re-visited | Comments / Notes | 1 = complete 2 = pending 3 = completed;no final cost
8100 | Vermont | LA 90044 | vacant lot - Vermont Miracle Park | 8 |  | weed,fence, trash,sign |  |  |  | 6126.89 | 2014-07-14 |  | COMPLETED - 7/17/14 | 1
4230 | Coldwater Canyon | Studio City 91604 | FS 78 | 2 | 2014-06-18 | trash, board-up, sign, secure gate |  |  |  | 6232.2 | 2014-07-16 | 2014-09-23 | COMPLETED - 7/16/14 CFD cost rpt 12/2/14 CFD cost rpt 04/30/15 | 1
610 | California Ave | Venice 90291 | Vera Davis Ctr | 11 | 2014-07-16 | Weed Abatement/Trash Removal |  |  |  | 4357.16 | 2014-07-24 |  | COMPLETED - 7/24/14 | 1
2254 | 103rd St | LA 90002 | vacant lot | 15 | 2014-07-01 | Weed, trash removal | CD 15 |  |  | 2807.15 | 2014-07-30 |  | COMPLETED - 7/30/14 | 1
510 | Venice Blvd | Venice 90291 | vacant lot | 11 | 2014-07-17 | Remove homeless, debris and property, signage |  |  |  | 6819.02 | 2014-08-05 |  | COMPLETED - 8/5/14 | 1
5001 | Balboa Blvd | Encino 91316 | FS 83 | 5 | 2014-09-30 | fence, board-up, possible interior asbestos removal, graffitti, weed, trash | City Atty Raffy Astvasadoorian | 2014-10-06 | 3410 | 3733.97 | 2014-08-07 | 2014-10-02 | $3,410 estimatefor fence and board-up only. Rec'd 10/7/14 CFD cost rpt 11/4/14 | 1
5001 | Balboa Blvd | Encino 91316 | FS 83 | 5 | 2014-07-21 | Secure Windows, board-ups | City Atty Raffy Astvasadoorian |  |  | 987.26 | 2014-08-07 | 2014-09-30 | COMPLETED - 8/7/14 CFD rpt 11/4/14 | 1
300 | Mount Holyoke | LA 90272 | street intersection | 11 | 2014-07-16 | Fix broken gate, fencing |  |  |  | 2126.26 | 2014-08-07 |  | COMPLETED - 8/7/14 CFD rpt 12/31/14 | 1
970-1010 | Jefferson Blvd | LA 90011 | Paul Williams / Angelus Funeral | 9 | 2014-08-11 | graffiti, weed,fencing, trash removal, board-up, signs |  |  |  | 12085.34 | 2014-08-14 |  | COMPLETED - 8/14/14 cost came from Rose 9/29/14 rpt cost came from 04/30/15 | 1
4255 | Olive St | LA 90037 | old Junipero Serra Library | 9 | 2014-08-11 | graffiti, weed, trash,sign, board-ups |  |  |  | 9879.96 | 2014-08-14 | 2014-12-03 | COMPLETED 8/14/14 cost came from CFD 12/31/14 rpt 12/2/14 - DP confirmed completion | 2
949 | Carondolet | LA 90006 | vacant lot | 1 | 2014-07-04 | Remove homeless, weeds, fencing, trash, signage |  |  |  | 14200.42 | 2014-08-17 |  | COMPLETED - 8/17/14 CFD cost report 12/31/14 CFD cost report 04/30/15 | 1
6621 | Manchester | Westchester 90045 | FS 5 | 11 | 2014-08-11 | Tree trimming, grafitti, weed, signage, board-up, fence repair, clean-up, |  |  |  | 13089.12 | 2014-09-24 |  | Completed - 9/24/14 per David Perka. Cost from Rose 9/29/14 rpt but w/o tree trimming & board-up 10/7/14 - req to ID any work needed for bldg for possible tenant. | 1
550 | Ramirez St | LA 90012 | LAPD parking lot | 14 | 9/3/2014 9/22/2014 | weed,trash |  |  |  | 1372.87 | 2014-09-29 | 2014-10-21 | COMPLETED 9/29/14 CFD rpt 11/4/14 10/22/14 - responded to Peter's email to revisit in Nov. | 1
1206 | Vermont |  | FS 13 | 1 | 2014-04-21 | Interior/Exterior Cleanup and Securing premises |  |  |  | 5784.65 | 2014-09-29 |  | COMPLETED cost came from Rose 9/29/14 rpt | 1
5965 | St Andrew Place | LA 90047 | APN 6001-013-906 old temp site for 77th PD | 8 | 2013-10-15 | Overgrown vegetation removal |  |  |  | 292.88 | 2014-10-02 |  | CFD rpt 11/4/14 - labor only 1/12/15 - completed per PI CFD rpt 1/31/15 | 1
4958 | Cahuenga | NH 91601 |  | 4 | none | Re-Visit inspection | n/a |  |  | 104.22 | 2014-10-09 |  | Cost from 10/9/2014;12/31/14 rpt | 1
1525 | 103rd St | LA 90002 | FS 65 | 15 | 2014-07-29 | weed, trash, fencing, |  |  |  | 4470.24 | 2014-10-14 | 2014-09-04 | COMPLETED - 7/30/14 | 1
2254 | 103rd St | LA 90002 | vacant lot | 15 | 2014-09-22 | install fence, install sign; clear trash. | CD 15 |  | 3675 | 2986.98 | 2014-10-14 |  | 9/24/14 - estimate recd COMPLETED - 10/10/14 | 1
12560 | San Fernando Rd | Sylmar 91342 | APN 2506-034-900 | 7 | 2013-10-07 | sign, homeless removal, clean-up |  |  |  | 223.39 | 2014-10-23 |  | CFD rpt 11/4/14 - labor only 1/12/15 - completed per PI CFD rpt - 1/31/15 | 1
3612 | 11th Ave | LA 90018 | SLA Animal Shelter | 10 | 2014-09-07 | board-up, sign, dumping, repair roll-up garage door | Dept. of Animal Services |  | $353.98 - invoice garage door repair only | 2665.5 | 2014-10-26 |  | 9/25/14 - roll up garage door repair finished per Mark. 10/26/14 - signage installed | 1
11950 | Missouri Avenue | LA 90025 | WLA Animal Shelter | 11 | 2014-09-22 | sign, fence repair, 2 trees trimming, 1 tree to be removed. No squatters present. | Dept. of Animal Services |  | 18783 | 13526.18 | 2014-11-03 |  | 9/25/14 - estimate recd Cost rpt 11/4/14 weed,fence trash only 11/17/14 - told David to trim trees only, no tree removal and no sidewalk repair. 1/12/15 - completed per PI CFD rpt - 1/31/15; 4/30/15; 6/30/15 | 1
5975 | Western Ave | LA 90047 | vacant lot | 8 | 2014-09-04 | fence |  | 2014-09-04 |  | 939.29 | 2014-11-04 | 2014-10-21 | COMPLETED. CFD rpt 11/4/14 | 1
5975 | Western Ave | LA 90047 | vacant lot | 8 | 2014-10-21 | weed, trash, |  | 2014-10-21 | 1045 | 2851.71 | 2014-11-04 |  | COMPLETED. CFD rpt 11/4/14 | 1
956 | 81st St | LA 90044 | APN 6032-005-900 vacant lot | 8 | 2014-10-03 | Tree from property is hitting roof of 8110 Vermont Ave. Tree removal/trimmed |  |  |  | 342.72 | 2014-11-06 |  | CFD rpt 11/4/14 labor only 1/12/15 - completed per PI | 1
5001 | Balboa Blvd | Encino 91316 | FS 83 | 5 | 2014-10-01 | re-secure front door, cover hole in roof, additional fencing, re-post asbestos sign. | CA Neighborhood Prosecutor Raffy Astvasadoorian | 2014-10-02 | 6050 | 1700.36 | 2014-11-08 |  | 10/2/14 - Transients have been removing copper water piping & wiring per Peter. 10/2/14 - Estimate received. 1/12/15 - completed per PI CFD cost report - 04/30/15 | 1
11514 | Willowbrook | LA 90059 | vacant lot | 15 | 2014-10-28 | weed, car & trash removal, auction prep | RES | 2014-10-28 |  | 0.001 | 2014-11-12 |  | auction clean-upper David Perka email of 110614 - clean will be finished today COMPLETED - 11/12/14 CFD rpt 12/2/14; 12/31/14 cost of $3,019.37 clean-up paid by auction proceeds | 1
2916 | Beachwood | Hollywood 90068 | SFR | 4 | 2014-10-21 | exterior and interior clean up, access | RES | 2014-10-21 | 5629 | 0.01 | 2014-11-17 |  | Open house/auction 11/6/14 - bathroom cleaned 11/17/14 - per David Perka, work completed. CFD cost rpt 12/31/14; 1/31/15 2/1/15 - requested front yard cleanup; leaves, weeds CFD cost rport 04/30/15 - $11,053.75 CFD to be reimbursed through sale proceeds. Notice of completion sent to Acct 05/06/15. | 1
4230 | Coldwater Canyon | Studio City 91604 | FS 78 | 2 | 2014-10-28 | graffitti removal | CFD |  | 750 | 643.38 | 2014-11-20 |  | CFD cost report 11/4/14; 1/31/15 1/12/15 - completed per PI | 3
1309 | Isabel st | LA 90065 | vacant lot | 1 | 2014-10-28 | weed, trash removal, auction prep | RES | 2014-10-28 |  | 0.001 | 2014-12-01 |  | CFD rpt 12/2/14; 12/31/14; 1/31/15 cost of $798.62 clean-up paid by auctionproceeds | 2
1704 | Jefferson Blvd | LA 90007 | vacant lot | 8 | 2014-10-28 | weed, trash removal, auction prep | RES | 2014-10-28 |  | 0.001 | 2014-12-01 |  | CFD rpt 12/2/14; 12/31/14; 1/31/15 cost of $501.65 clean-up paid by auction proceeds | 1
3646-3650 | Knobhill | Sherman Oaks | vacant lot | 4 | 2014-03-25 | weed, fencing, trash cleanup |  |  | 17820 | 13851.51 | 2014-12-01 |  | quote rec'd 10/28 CFD rpt 9/29/14 labor cost only 12/1/14 - per DP completed CFD rpt 12/2/14; 12/31/14; 1/31/15; 04/30/15
520 | Venice way | Venice 90291 | vacant lot | 11 | 2014-10-28 | weed, trash removal, auction prep | RES | 2014-10-28 |  | 0.001 | 2014-12-01 |  | Cost of $2,366.53 clean-up paid by auction proceeds | 1
6621 | Manchester | Westchester 90045 | FS 5 | 8 | 2014-10-22 | Procedure 5 Asbestos removal study | RES | 2014-10-22 | 700 | 1664.94 | 2014-12-02 |  | 11/5/14 - estimate recd COMPLETED - from CFD rpt 12/2/14; 1/31/15 | 1
22345 | Malden Avenue | Chatsworth 91304 | vacant lot | 12 | 2013-11-20 | Rodents |  |  |  | 641.8 | 2014-12-03 |  | CFD rpt 12/2/14; 12/31/14; 1/31/15 1/12/15 - completed per PI | 1
3311 | Thatcher | Venice 90292 | vacant Street Maintenance yard | 11 | 2014-11-19 | secure facility, homeless, fence | ​Marsha Jackson, Street Services Investigator | 2014-11-20 | 31050 | 630.88 | 2014-12-09 |  | CFD rpt 12/2/14 12/9/14 - estimate rec'd CFD rpt 12/31/14 1/12/15 - completed per PI | 1
501 | Mesa St | San Pedro 90731 | Neigh Hsng Service of LA | 15 | 2014-02-12 | Graffiti, weed, clean-up |  |  | 12210 | 7828.48 | 2014-12-15 |  | quote rec'd 10/30/14 for $12,210 incl trim 6 trees; JM told CFD do not trim trees. CFD rpt 12/2/14 - labor only 12/2/14 - per DP clean-up started and painting to follow 12/15/14 - per DP work completed. CFD rpt 12/31/14; 1/31/15 | 1
503 | Broad Ave | wilmington 90744 | vacant lot | 15 | 2014-10-22 | signage, homeless removal, weed, fence | Gabriela Medina, CD 15 | 2014-10-22 | 7068 | 1733.5 | 2014-12-22 |  | need quote cost for labor only 10/9/14 rpt fence installation scheduled for 12/15/14. fence and clean up finished on 12/22/14 CFD rpt 12/31/14; 1/31/15 | 1
970-1010 | Jefferson Blvd | LA 90011 | Paul Williams/Angelus Funeral Home | 9 | 2014-08-19 | Fence repair |  |  |  | 1591.55 | 2014-12-31 |  | CFD cost report 12/31/14 | 1
22322 | Napa | Chatsworth 91304 | vacant lot | 12 |  | Rodents |  |  |  | 292.87 | 2015-01-12 |  | CFD rpt 11/4/14 - labor only; 1/31/15 1/12/15 - completed per PI; no rodents | 1
15733 | Pacific Coast Hwy | Pacific Palisades 90272 | vacant lot | 11 | 2014-07-22 | Graffiti Removal |  |  |  | 0 | 2015-01-12 |  | COMPLETED; need cost 1/12/15 - completed per PI; | 1
3233 | Thatcher |  | Sanitation | 11 |  | demolish building | Paul Blausman, Sanitation |  |  | 630.88 | 2015-01-12 |  | 1/12/15 - per PI, CFD rec'd work order requesting estimate to demolish building. Sanitation will seek funding. Est sent to DOS. CFD rpt 1/31/15 -labor only | 1
421 | Ave 19 | LA 90031 | Old Lincoln Heights Jail | 1 | 2014-10-06 | secure building, change locks, 24 hr security officer $18K/month , port-a-potty $60/month | RES |  |  | 0 | 2015-01-30 |  | 10/8/14 - security ordered; 10/9/14 -port-a-potty to be delivered; Security: Oct. invoice $14,430.40; Nov invoice $18,332.61; Dec inv $18,474.42; Jan inv $18,709.14 = TOTAL =$69,946.57 PAID THRU RES 3040 ACCT | 1
421 | Ave 19 | LA 90031 | Old Lincoln Heights Jail | 1 | 2014-10-20 | Phase 5 study, remove items inside building, remove trash, fire extinguisher, locks, board-up | RES per LAFD citation | 2014-11-24 | $42,151 for 1st floor asbestos removal only | 68029.89 | 2015-01-30 |  | 10/22/14 - rec'd asbestos estimate $42,151. Tony approved work to proceed but Melody needs to figure out funding source. 10/23/14 - MM ok work to proceed. asbestos removal tent .finished by 11/11/14. No access allowed. 11/4/14 - asbestos P5 clean-up complete for 1st floor only. Basement NOT done due to no funding of $548,845. 12/11/14 - per Peter, fire extinguisher replaced. Board-up will begin when movers are finished. Per GM Tony, install alarm system then remove security officer. CFD rpt 12/31/14 - $68,029.89 ASBESTOS FIRST FLOOR CLEAN-UP COMPLETED 1/21/15 - LAFD John Vidovich email saying that fire watch can end when bldg is boarded-up. 1/12/15 - in progress per PI | 1
1269 | Ozeta Terrace (Ozeta & Clark St) | LA 90069 | vacant lot | 4 | 2015-01-12 | post signs | RES-DR | 2015-01-12 | 2580 | 1131.96 | 2015-02-02 |  | 1/13/15 - est rec'd 2/2/15 - project completed per Peter | 1
3642 | Roseview Ave | LA 90065 | vacant lot | 1 | 2014-12-29 | Repair or replace fence | Mel Ilomin, CD 1 | 2014-12-29 | 2155 | 2916.2 | 2015-02-02 |  | 1/12/15 - in progress per PI 1/21/15 - Mel Ilomin emailed stating work has begun. 2/2/15 - completed per DP | 1
0 | Washington Blvd/53rd St/Santa Fe | LA 90058 | vacant lot | 14 | 2015-01-22 | Sign Installation Request_No Trespassing & No Illegal Dumping | CD 14 Miguel Vargas/LAPD Ofcr Mark Hyland | 2015-01-22 |  | 1350.73 | 2015-02-02 |  | The location is near the Santa Fe Ave and Washington Blvd. intersection. The site is directly adjacent to the Santa Fe Ave bridge, on the east side and just south of 23rd Street. CFD rpt 1/31/15; 04/30/15 | 1
438 | Mesa St | San Pedro 90731 | FS 53 | 15 | 2015-01-06 | graffitti, weed, trash, sign, board-up, trim trees, fence | LABS Insp Robert Wood | 2015-01-06 | 7696 | 9484.58 | 2015-02-23 |  | 1/5/15 - R. Wood said he received a CSR about citizen complaint that he will send. 1/12/15 - in progress per PI 1/13/15 - est rec'd CFD rpt - 1/31/15 2/12/15 - per DP, tree trimming scheduled for 2/13/15; then work will be completed. 2/23/15 - DP tree trimmed CFD cost rpt 04/30/15 | 1
0 | Avenue 35 & Pasadena City APN: 5205004900 LA Metro APN: 5205004903 | LA | vacant lot | 1 | 2015-02-12 | fence, sign, weeds, trash clean-up, Homeless clean-up | Jose Rodriguez, CD1 | 2015-02-12 | 8652 | 8826.93 | 2015-03-23 |  | APN: 5205003900, 5205003901, 5205002901 (rear of Animal Services), and 5205003900 (rear of open space) CD 1 clean up will start 2/24 & 2/26. Jose cell 213-785-4896. 2/23/15 - per Tom, permanent fence with gate. 2/25/15 - estimate received; Fencing to be installed on 2/27/15. 3/9/15 - CFD to proceed with "de-grubbing: 3/23/15 - work completed per Peter. | 1
970-1010 | Jefferson Blvd | LA |  | 9 | 2015-03-09 | Remove Trash , remove grafiti & remove weeds/overgrown brush inside and surrounding the buildilng on both sides of street. | Nora Gutierrez, CD 9 | 2015-03-06 | 4625 | 555 | 2015-03-31 |  | 3/11//15 - cost estimate rec'd and informed CD 9. CFD rpt 05/31/15. | 2
3612 | 11th Ave | LA 90018 | SLA Animal Shelter | 10 | 2015-04-09 | lock doors, secure facility, signs, boardups | Maria Gordo, Dept of Animal Services | 2015-04-09 |  | 3503.56 | 2015-04-14 |  | 4/14/15 - email from Peter. Bldg secure, no homeless person; electricity still on. 4/23/15 - DWP Thom Breckner (213) 367-3497; service should be off but needs confirmation. | 1
5001 | Balboa Blvd | Encino 91316 | FS 83 | 5 | 2015-04-09 | homeless, weed, fence | Noah Mulstein, CD 5 | 2015-04-09 |  |  | 2015-04-27 |  | 4/15/15 - Per Peter's email, clean up will begin 4/16/15 4/27/15 - compelted | 1
6353 | Lindley Avenue | Reseda 91355 | vacant lot APN 2124018905 | 3 | 2015-04-08 | fence installation, signs, weed abatement | Arielle Bernard, CD 3 | 2015-04-14 | 3580 | 5870.37 | 2015-04-30 |  | 4/20/15 - estimate rec'd. Total project cost with tree trimming $6,588. 4/27/15 - approve fence and sign installation. CFD cost rept 04/30/15; 5/31/15;6/30/15 | 1
4225 | Olive st | LA 90037 | old Junipero Serra Library | 9 | 2015-04-24 | Remove homeless | ​Paloma Pérez-McEvoy, Deputy Chief of Staff and Counsel Councilman Curren Price - CD 9 | 2015-04-29 | 0 | 116.87 | 2015-05-04 |  | 5/4/15 - per DP, FYI, the individual in question is on sidewalk and steps in front of, please advise, hes not actually inside or within the front porch, he wasnt there when checked it. The gate and building is still secured. CFD cost rpt 5/31/15 - site visit only. | 1
421 | Ave 19 | LA | Old Lincoln Heights Jail | 1 |  | Phase 5 study | RES, CFD, Val | 2015-04-20 | 49931 |  | 2015-05-06 |  | 5/6/15 -1st floor asbestos clean-up completed per PI. | 3
749 | Manchester | LA | FS 57 | 8 | 2015-04-23 | fence repair, | Berny Moto, CD 8 | 2015-04-23 | 495.95 | 495.95 | 2015-05-07 |  | Possible next door renter: AA Motors, Anderson @ 323-750-8891 4/28/15 - estimate received CFD rpt 6/30/15 | 1
412 | Paseo Miramar | Pacific Palisades | vacant lot | 11 | 2015-04-16 | install warning signs | Eric Noreen, BOE | 2015-04-16 | 1881 | 1072.75 | 2015-05-07 |  | 4/28/15 - CFD estrimate received CFD cost rpt 04/30/15 - partial 5/7/15 - signs installed 5/8/15 - 4th CPR funding request submitted to CAO; CAO did not include in 4th CPR CFD rpt 6/30/15 | 1
15329 | De Pauw | Pacific Palisades 90272 | SFR | 11 | 2015-01-28 | weed, trash, | RES | 2015-01-28 |  | 0.001 | 2015-05-11 |  | 5/11/15 - work completed. DP sent pictures. Cost of $5,563.88 clean-up to be paid by auction proceeds. CFD cost rpt 6/30/15 | 2
15333 | De Pauw | Pacific Palisades 90273 | SFR | 11 | 2015-01-28 | install sign, clean-up, weed, grafitti, boarod-up | RES | 2015-01-28 |  | 0.001 | 2015-05-11 |  | CFD cost rpt 04/30/15 5/11/15 - work completed. DP sent pictures. Cost not yet final. CFD cst rpt 5/31/15; 6/30/15 Cost of $6,634.40 clean-up to be paid thru auction proceeds | 1
15333 | De Pauw | Pacific Palisades | SFR | 11 | 2015-03-11 | graffiti, board-up | Robert Wood, LADBS | 2015-03-11 |  | 0 | 2015-05-11 |  | Cfd cost rpt 04/30/15; 6/30/15 5/11/15 - work completed. DP sent pictures. Cost not yet final. Cost of $1,344.00 clean-up to be paid thru auction sale proceeds | 1
18777 | Eldeen Drive | Tarzana | vacant lot | 3 | 2015-04-28 | fence repair, weed abatement | Arielle Bernard, CD 3 | 2015-04-28 |  | 3058.46 | 2015-05-12 |  | 5/12/15 - DP called stating LAFD contract was on site. Told DP to let LAFD finish work. 5/18/15 -return call from LAFD Insp. Sanz-Agero completed by LAFD Fire Brush Clearance Unit (818) 778-4924. LAFD will not send bill to GSD.He said they have been maintaining the lot for over 10 years. 6/1/15 - DP emailed pictures. CFD cost rpt 5/31/15; 6/30/15 | 1
3671 | Vermont Ave - South | LA | Bethune Library |  | 2015-03-06 | CRA property transfer of fence rental to GSD | Josh Rohmer, CAO Janeth Estrada, CRA | n/a |  | 141 | 2015-05-19 |  | 3/6/15 United Site Services (800-864-5387, Rosemary is ext. 6287) is expecting the call from the City to transfer the service. United has some difficulty identifying the property using the correct address (3671 or 3685 S. Vermont Ave.) CRA/LA's Customer ID: USS-179096, and the most recent work order in 0-597310. If possible, please try to contact them early next week - otherwise CRA/LA plans to have them remove the fence, at which point we'd need to have it re-installed, which would be a waste. 3/9/15 - called fencing company and transferred billing to GSD-RES. Account No LAX-38899 - Order No. LO-597310 5/19/15 - March invoice received in the amount of $141.00 forwarded by CRA.
421 | Ave 19 | LA | Old Lincoln Heights Jail | 1 | 2015-04-27 | 24/7 security services | Val/Melody | 2015-04-27 |  |  | 2015-05-31 |  | G4Secure Solutions security from 4/27/15-5/31/15 $18,245.32 PAID THRU RES 3040 ACCT | 1
1525 | 103rd St | LA 90002 | FS 65 | 15 | 2015-04-13 | remove/clean-up bird nestings and bee hives | LAFD - Emily Gutierrez | 2015-04-13 | 7353 | 550.5 | 2015-06-01 |  | 4/29/15 - est rec'd 5/13/15 - per DP, vendor Cats will be on site 5/26 & 27/15 to address the requested mitigations. | 1
421 | Ave 19 | LA 90031 | Old Lincoln Heights Jail | 1 | 2015-02-02 | ITA to install alarm and videos with LAPD monitoring | GSD GM | 2015-02-02 | 42777.44 | 0 | 2015-06-05 |  | $42,035.44 from ITA and $742 for GSD to move electrical outlet 2/20/15 - Per Donna of CAO, will use Fund 100, Department 54, Account 00L046 entitled Citywide Maintenance and Improvements for CSR 40-01639 Ref# MIS-15-075 - Lincoln Heights Jail Security System. Paid thru 3rd CPR | 1
0 | Browns Canyon Silo APN 2821-002-900 12080 BROWNS CANYON RD | Chatsworth 91311 | vacant lot | 12 | 2015-02-03 | fence repair, cap silos | LACounty Public Works Eng Insp John McCarney | 2015-02-03 | 94155 | 0.001 | 2015-06-09 |  | 2/5/15 - estimate received 5/8/15 - 4th CPR request submitted to CAO. 5/18/15 - per Raoul, request submitted for inclusion in 4th CPR. 6/9/15 - CCouncil approved 4th CPR; CF 14-1284-S3 | 1
421 | Ave 19 | LA | Old Lincoln Heights Jail |  | 2015-06-08 | DWP lights installation | LAPD |  | 5000 |  | 2015-06-22 |  | 6/11/15 - email from Thom Breckner 5 light posts will be installed 6/20/15 $5,000 PAID THRU RES ACCT | 1
421 | Ave 19 | LA | Old Lincoln Heights Jail | 1 | 2015-06-05 | replace dual tech motion detector for outside and install new flood detector for basement. | ITA Jerry Morris |  | 229.65 |  | 2015-06-24 |  | break-ins/vandalism 6/9/15 - Lisa H sent PO to Acctg created PO. Estimate from FFS Technology $229.65 PAID THRU RES ACCT | 1
421 | Ave 19 | LA | Old Lincoln Heights Jail | 1 | 2015-04-20 | board-up,secure door, trash, | SLO Manuel Elorriaga | 2015-04-20 |  | 46489.69 | 2015-06-30 | 4/20-4/29/15 | 4/21/15 - rec'd call from Peter. Facility got broken into again less than 24 hours after securing site. Multiple break-ins occurring every week. CFD rpt 6/30/15 total of $114,519.58 | 1
421 | Ave 19 | LA | Old Lincoln Heights jail |  | 2015-06-29 | ITA to replace (5) motion detectors and (2) shock sensors as a result of 6/25-6/29/ breakin. | ITA Jerry Morris | 2015-06-29 | 793.23 |  | 2015-07-03 |  | 6/29/15 - ITA to replace (5) motion detectors and (2) shock sensors as a result of 6/25-6/29/ break-in. Estimate received and PO to be created by Lisa. $793.23 PAID THRU RES ACCT | 1
| 4th & Santa Fe | LA 90058 | under the bridge | 14 | 2015-06-17 | No Loitering sign installation | City Atty Kurt Knecht Sergio Carvajal, CD14 | 2015-07-08 |  | 0 | 2015-07-08 |  | 7/7/15 - Per Joe Ramirez, location is under the jurisdiction of Street Services | 1
| 86th St & Broadway | LA | vacant lot | 8 | 2015-06-30 | clean-up trash, weed, RUSH job | Valerie Melloff/David Roberts | 2015-06-30 |  | 5855.83 | 2015-07-08 |  | Rush job due toLA Times inquiry. Later found out that property is under the control of DOT. 7/8/15 - PI completing work. 7/13/15 - Dave Perka emailed pictures of completed work. | 1
| Tupper & columbus Avenue | North Hills | vacant lot | 7 | 2015-06-22 | weed, trash, install fence | Cristina Coria & Yolanda Fuentes, CD 7 | 2015-06-22 | 12347 | 3691.09 | 2015-07-09 |  | 6/24/15 - estimate received from DP $2,549.90 estimate for fence only from Quality Fence Co. 6/30/15 - partial cost from CFD rpt 7/31/15 - CFD rpt | 1
| Ave 26 & Lacy | LA | vacant lot | 1 | 2015-06-02 | weed, fence, signs. | Jose Rodriguez of CD 1 | 2015-06-02 | 15115 | 20041.25 | 2015-07-13 |  | multi-city agency clean-up to be conducted on 6/25-26/15 APN: 5205003900, 5205003901, 5205002901 (rear of Animal Services), and 5205003900 (rear of open space) 6/30/15 CFD cost rpt 7/31/15 - CFD rpt | 1
749 | Manchester |  | FS 57 | 8 | 2015-05-26 | weed, trash, board-up, fence repair, homeless, debris, window breach, sign, graffitti | Berny Moto, CD 8 | 2015-05-26 |  | 14049.78 | 2015-07-14 |  | 5/11/15 - Dave Perka emails that fence is broken again. 5/26/15 - Berny followed-up. CFD cost rpt 6/30/15 7/7/15 -per PI fence to be completed on 7/13/15 | 3
749 | Manchester | LA 90044 | FS 57 | 8 | 2015-06-17 | Graffiti, weed, trash, board-up,sign,fencing, homeless | Bethel Wilson, City Atty Neighborhood Prosecutor | 2015-06-17 |  | 19333.19 | 2015-07-14 | 2015-04-16 | COMPLETED CFD cost rpt 11/4/14; 12/31/14 4/16/15 - Dave Perka advised that placed is trashed again. He gets calls from the car dealership next door about activities taking place in the building. Homeless cuts fences and the place cannot remain secure for a long time. | 1
412 | Paseo Miramar | Pacific Palisades 90272 | vacant lot | 11 | 2015-01-07 | trash chair removal | RES-JOC | 2015-01-07 |  | 859.3 | 2/3/2015 |  | CFD rpt 1/31/15;04/30/15; 6/30/15 | 1
421 | Ave 19 | LA | Old Lincoln Heights Jail | 1 | 2015-06-04 | Secure View Proposal - install window covering & maintenance | Val, Melody |  | 275100 |  |  |  | Secure View to submit proposal by June 15. Estimate received. Pending item. | 2
11253,11259, 11265, 11273 | Laurie Drive | LA 91604 | vacant lot | 2 | 2014-09-04 | Fence and repair work |  |  | 18602 | 69.48 |  |  | need quote. Not on Peter's list 1/12/15 - per PI est sent to RES. JM responded to put on hold; not priority. | 2
6621 | Manchester | LA 90045 | FS 5 | 11 | 2015-02-17 | trash cleanup, weeds | Nancy Aguilar, CD 11 & srogers@kentwoodhomeguardians.com | 2015-02-17 | 2560 | 985.59 |  |  | 2/25/15 - estimate received and sent to CD 11 04/30/15 CFD rpt (partial cost?) | 1
# OF JOBS YTD |  | 79
# OF JOBS COMPLETED |  | 75
# OF JOBS PENDING |  | 4
YTD EXPENSE: Completed & Pending |  | 367695.497
AVERAGE Expense: |  | 4654.3734
Completed work YTD Expense:
Pending Projects: Actual & Estimate
| TOTAL | 0
Note on A79: 103059: CD 2 may pay for work. Quote is needed.

## FY 15-16
Street # | Street Name | City & ZIP | Building Name | CD | Date of Request | Work Requested | Requested by: | To: CFD | Estimate | Cost | COMPLETED | Date Re-visited | Comments / Notes | 1 = complete 2 = pending 3 = completed;no final cost
421 | Ave 19 | LA | Old Lincoln Heights Jail | 1 | 2015-06-04 | Secure View Proposal - install window covering & maintenance | Val, Melody |  | 275100 |  |  |  | Secure View to submit proposal by June 15. Estimate received. Pending item.
421 | Ave 19 | LA | Lincoln Heights jail |  | 2015-06-29 | ITA to replace (5) motion detectors and (2) shock sensors as a result of 6/25-6/29/ breakin. | Jerry Morris, ITA |  |  | 793.23 | 2015-07-03 |  | 6/29/15 - ITA to replace (5) motion detectors and (2) shock sensors as a result of 6/25-6/29/ break-in. Estimate received and PO to be created by Lisa. ITA installed. | 1
421 | Avenue | LA | Lincoln Heights jail |  | 2015-07-07 | 12 hr shift for Security Services; | GSD-Val/Melody |  |  | 15639.95 |  |  | Service from July 7 thru Sept 30 8/24/15 - invoice for July $6,577.07 9/16/15 - invoice for August $9,062.88
| Ave 26 & Lacy | LA | vacant lot | 1 | 2015-06-02 | weed, fence, signs. | Jose Rodriguez, CD 1 |  |  | 20041.25 | 2015-07-13 |  | multi-city agency clean-up to be conducted on 6/25-26/15 APN: 5205003900, 5205003901, 5205002901 (rear of Animal Services), and 5205003900 (rear of open space) 7/13/15 - Peter emailed pictures of completed project. CFD cost rpt 07/31/15 | 1
749 | Manchester | LA | FS 57 | 8 | 2015-04-23 | fence repair, | Berny Moto, CD 8 | 2015-04-23 | 495.95 | 495.95 | 2015-07-14 |  | Possible next door renter: AA Motors, Anderson @ 323-750-8891 4/28/15 - estimate received CFD rpt 6/30/15 7/14/15 - DP emailed completed pictures. | 1
749 | Manchester | LA | FS 57 | 8 | 2015-05-12 | fence repair, homeless, debris, window breach, sign, graffitti | Berny Moto, CD 8 | 2015-05-26 |  | 2314.78 | 2015-07-14 |  | 5/11/15 - Dave Perka emails that fence is broken again. 5/26/15 - Berny followed-up. CFD cost rpt 6/30/15 7/7/15 -per PI fence to be completed on 7/13/15 | 1
749 | Manchester | LA | FS 57 | 8 | 2015-06-17 | homeless, clean-up, fence, board-up, chain-link gate, rolling gate, security bars, grafitti | Bethelwel Wilson, City Atty Neighborhood Prosecutor | 2015-06-17 | 23196 | 14049.78 | 2015-07-14 |  | 7/14/15 - DP emailed completed pictures. Notifed CA work completed. CFD cost rpt 07/31/15 | 1
6621 | Manchester | LA 90045 | FS 5 | 11 | 2015-02-17 | trash cleanup, weeds | Nancy Aguilar, CD 11 srogers@kentwoodhomeguardians.com | 2015-02-17 | 2560 | 985.59 | 2015-08-19 |  | 2/25/15 - estimate received and sent to CD 11 04/30/15 CFD rpt (partial cost?) | 1
| Tupper & columbus Ave | North Hills | vacant lot | 7 | 2015-06-22 | weed, trash, install fence | Cristina Coria & Yolanda Fuentes, CD 7 | 2015-06-22 | 12347 | 859.22 | 2015-07-09 |  | 6/24/15 - estimate received from DP $2,549.90 estimate for fence only from Quality Fence Co. 6/30/15 - partial cost from CFD rpt 7/9/15 - DP emailed pictures. Notified CD 7 work completed. | 1
3671 | Vermont Ave - South | LA | Bethune Library |  | 2015-03-06 | CRA property transfer of fence rental to GSD | Josh Rohmer, CAO | n/a |  |  |  |  | 3/6/15 Jacqueline - Thank you for working on this. FYI, United Site Services (800-864-5387, Rosemary is ext. 6287) is expecting the call from the City to transfer the service. United has some difficulty identifying the property using the correct address (3671 or 3685 S. Vermont Ave.) so it may be easiest for them to search for the record using CRA/LA's Customer ID: USS-179096, and the most recent work order in 0-597310. If possible, please try to contact them early next week - otherwise CRA/LA plans to have them remove the fence, at which point we'd need to have it re-installed, which would be a waste. 3/9/15 - called fencing company and transferred billing to GSD-RES; monthly invoice approximately $141.
361 | S. Hill Street | LA | Bunker Hill - Parcel Y - Angeles Knoll | 14 | 2015-07-08 | broken fence | Todd Hessick, GSD Special Events | 2015-07-08 | 1452 | 1885.22 | 2015-08-03 |  | 7/13/15 - estimate received 8/3/15 - DP completed CFD rpt 073115
| APN 2784002902. |  | Northridge Metrolink Station |  | 2015-07-22 | install "No Trespassing" sign | Alin Sahagian, Deputy City Atty (818) 374-6837 |  |  |  | 2015-07-23 |  | Joe checked Assessor's Book 2784 Page 2 Parcel 902 and I came up with a quitclaim deed which recorded on June 23, 1978 as instrument No. 78-684301 of Official Records. According to the Certificate of Acceptance, this property belongs to the Department of Recreation and Parks. The adjacent parcel (2784-2-903) belongs to the Los Angeles County Flood Control Distric | 1
14123 | Nordhoff |  | old FS# 7 | 6 | 2015-07-27 | homeless encampment, secure facility | Curt Klafta/Emily Gutierrez, LAFD Gene Paleno, citizen | 2015-07-28 | 5820 | 637.75 |  |  | 7/27/15 - Emily Gutierrez email - On this date/time LAPD was contacted to respond to old FS-7; this information came to Fire Facilities via BC C. Combs (LAPD Inc#2522). Chief Combs reported that it was apparent that there was a homeless encampment on the property; additionally, there appears to be water running from the apparatus floor to the street. As discussed last week, the property needs to be secured as quickly as possibly; even more so now that there is unauthorized use of City utilities. CFD rpt 7/31/15
1803 | Arlington |  | Washington Irving Library | 10 | 2015-07-23 | create one time purchase order for Intuitive Real Estate Solutions (Secure View) | Tony Royster/Val Melloff, GSD | 2015-07-29 | 6435 |  |  |  | 7/23/15 - Secure View proposal $6,435 7/30/15 - sent email to Connie Espina, GSD Procurement 8/5/15 - Requisition in SMS
| Ave 49 thru Ave 52 |  | Sycamore Grove Park | 1 | 2015-07-29 | signs, fencing, T gate, weed abatement | Jose Rodriguez, CD 1 | 2015-07-29 |  | 69.64 |  |  | 7/29/15 - site visit & walk-thru with CD 1,LAPD & RAP 8/4/15 - site visit with CFD
15329 | De Pauw | Pacific Palisades |  | 11 | 2015-08-03 | gate vandalized | Wallace Leifer, neighbor | 2015-08-03 |  |  |  |  | The front gate on the right has been broken & vandals get around to the back. Please check all gates @ both properties & also see if there has been additional entry from the back into the homes!
1631 | E 110TH | LA 90059 | vacant lot | 15 | 2015-08-03 | fire brush clearance | Nicole Wells, CD 15 | 2015-08-04 | 3090 |  |  |  | 8/11/15 - estimate rec'd
11950 | Missouri | LA 90025 | Old West Animal Shelter | 11 | 2015-08-04 | graffitti | Dave Paschal, GSD | 2015-08-04 | 7896 |  | 2015-08-21 |  | 8/4/15 - Inspected by Rodolfo A Esqueda then reported to David Paschal 8/5/15 - estimate received
14123 | Nordhoff |  | FS 7 | 6 | 2015-08-07 | remove homeless, install fence, sign, board-up | Lorena Bernal CD 6 | 2015-08-07 | 495 |  |  |  | 8/11/15 - fence to be installed 08/13/15
749 | Manchester | LA | FS 57 | 8 | 2015-08-06 | quote to demolish building, fencing | Solomon Rivera, CD8 | 2015-08-06 | 82835 |  |  |  | CD 8 request made on 8/6/15 mtg
6621 | W 85TH PL | LA 90045 |  | 11 | 2015-08-11 | weeds, trash | 3-1-1- Service Request ID : 00184759 | 2015-08-11
1525 | 103rd Street |  | FS 65 | 15 | 2015-08-19 | stolen copper pipes, fix water pipes, estimate to separate utility meter with YoWatts, secure facility | Heather Anderson/Lorena Arellano CD 15; McCormick/Cooper-GSD | 2015-08-25 | 1250.09 |  |  |  | Estimate is for recapping copper pipes only.
4630 | Griffin Avenue | LA 90031 |  | 1 | 2015-08-27 | fence, sign | Melinda Ramos-Alatorree, CD 1 | 2015-08-27 |  | 0 | 2015-09-01 |  | Google map shows it’s the continuation of Ave 52-Sycamore Grove Park. Need to verify. 9/1/15 - Property belongs to RAP, per Joe. Canceled work order to CFD. Informed CD 1.
| 94th & Broadway |  | APN: 6053-006-926 |  | 2015-08-27 | clean-up | solomon Rivera, CD 8 | 2015-08-27 |  | 0 | 2015-08-31 |  | 8/31/15 - Joe researched property belongs to HCIDLA. Informed CD 8 & HCID Vasken& Doug. CFD request canceled.
|  | Chatsworth | Nike Browns Canyon silo |  | 2015-09-02 | broken roof cap; cap roof with lite weight concrete | Thom Bylard/Michael Loaiza | 2015-09-02 | 11984 |  | 2015-09-21 |  | 9/2/15 - not part of original estimate since roof was not broken at that time. Change order submitted by CFD.
1803 | Arlington |  | Old Washington Library | 8 | 2015-09-14 | trash pick-up, clean-up | GSD/Melody/ | 2015-09-14 |  |  | 2015-09-17
1803 | Arlington | LA | Old Washington Library | 8 | 2015-07-23 | Secure View Proposal - install window covering & maintenance | Tony/Val |  | 6753 | 6753 | 2015-09-14 |  | 7/23/15 - issue one time PO to Intuitive Real Estate Solutions per tony 8/10/15 - PO issued by Connie Espinosa
# OF JOBS YTD |  | 19
# OF JOBS COMPLETED |  | 9
# OF JOBS PENDING |  | 10
YTD EXPENSE: Completed & Pending |  | 57702.72 |  |  |  | Completed work YTD Expense:
AVERAGE Expense: |  | 3036.9853 |  |  |  | Pending Projects: Actual & Estimate
[6 empty] | TOTAL | 0